## Sheet1
Bids Register
Reporting Period : |  | 2019/2020
Name of Municipality |  | Mohokare Local Municipality
Bid Committee Meeting Dates
End User | Bid nr. | Goods,Infrastructure Projects ,Service Description | Advert Date | Compulsory Briefing Session | Closing Date | Specification Committee | Evaluation Committee | Adjudication Committee | Award Date | Name Of Bidder Awarded | Amount (Excl. VAT)
July
Technical Services | SCM/MOH/08/2019 | Construction and Equiping of Abstraction works on the Orange River and Equipping of 2 Raw Water Pump Stations with M&E | 05/07/2019 | 12/07/2019 | 02/07/2019 | 04/07/2019 | 23/10/2019 | 24/10/2019 | 24/10/2019 | Gaberton Investment (Pty) Ltd | 33152309.84
Finance | SCM/MOH/09/2019 | Recover of Unpaid Traffic Fines | 26/07/2019 | 02/08/2019 | 16/08/2019 | 24/07/2019 | Not yet held | 09/12/2019 | 09/12/2019 | Katlego Capital (Pty) Ltd | 23%
Finance | SCM/MOH/10/2019 | Source of funding and do business processes Assessments and Audit for Mohokare Local Municipality-MSCOA Compliance 2019/2020 | 26/08/2019 | 02/08/2019 | 27/08/2019 | 24/08/2019 | Not yet held | Not yet held | Not yet awarded
August
Finance | SCM/MOH/11/2019 | Panel of suppliers to repair and maintain municipal vehicles | 06/09/2019 | 18/09/2019 | 26/09/2019 | 16/09/2019 | Not yet held | Not yet held | Not yet awarded | Not yet awarded
Technical Services | SCM/MOH/12/2019 | Panel of contractors to repair and maintain water and waste water infrastructure plants for 3 years | 06/09/2019 | 18/09/2019 | 26/09/2019 | 03/09/2019 | Not yet held | Not yet held | Not yet awarded | Not yet awarded
Technical Services | SCM/MOH/13/2019 | Supply and Installation pf backup generator | 06/09/2019 | 18/09/2019 | 26/09/2019 | 03/09/2019 | 08/11/2019 | 09/12/2019 | 09/12/2019 | Masala Ramabulana Holdings | 605381.74
Finance | SCM/MOH/14/2019 | Insurance for 3 years | 06/09/2019 | 19/09/2019 | 27/09/2019 | 04/09/2019 | 05/10/2019 | 06/11/2019 | 06/11/2019 | AON | 725035.72
Technical Services | SCM/MOH/15/2019 | Panel of suppliers for the hiring of plant equipment for 3 years | 06/09/2019 | 19/09/2019 | 27/09/2019 | 04/09/2019 | 19/11/2019 | 28/11/2019 | 29/11/2019 | 1. Pokomane Trading, 2 Mashiya Projects, 3. Xmoor Transport (Pty)Ltd/Plant Hire, 4. Ekene Investments Cc, 5. Aqua Transport and Plant Hire (Pty) Ltd, 6. Nokoane Services, 7. Amadwala Construction Trading, 8. Tanosa Group, 9. Tru Build
Technical Services | SCM/MOH/16/2019 | Appointment of service provider to do water sampling/resampling for 3 years | 06/09/2019 | 19/09/2019 | 27/09/2019 | 04/09/2019 | Not yet held | Not yet held | Not yet awarded | Not yet awarded
Corporate Services | SCM/MOH/17/2019 | Panel of suppliers to render legal services for 3 years | 06/09/2019 | 19/09/2019 | 26/09/2019 | 03/09/2019 | Not yet held | Not yet held | Not yet awarded | Not yet awarded
September
Technical | SCM/MOH/18/2019 | Zastron/Matlakeng: Upgrading of waste water pump stations & construction works of new outfall sewer line | 27/09/2019 | 04/10/2019 | 23/10/2019 | 25/09/2019 |  | 27/11/2019 | 27/11/2019 | Baile Trading (Pty) Ltd CUA Trio Holdings JV | 13404347.83
October | SCM/MOH/19/2019 | Supply and delivery of protective clothing | [5 empty] | 22/11/2019 | 22/11/2019 | Tangastep | 655494
November
December
| SCM/MOH/20/2019 | Appointent of Service providers for Source Funding | [6 empty] | Not yet awarded
January
| SCM/MOH/01/2020 | Rouxville/Roelelathunya Phase 2 Construction of 2.0 Km paved access roads with related storm water | 31/01/2020 | 07/02/2020 | 06/03/2020 | 29/03/2020 |  | 20/05/2020 |  | Project Pioneer JV Copa Del Rey Trading | 13350915.6
| SCM/MOH/02/2020 | Rouxville/Roelelathunya Upgrading of the Rouxville Waste Water Treatment Works (WWTW) Re-advert | 31/01/2020 | 07/02/2020 | 21/02/2020 | 29/01/2020 | Not yet held | Not yet held | Not yet awraded
| SCM/MOH/03/2020 | Fleet Management System For 3 years | 31/01/2020 | 06/02/2020 | 21/02/2020 | 29/01/2020 | Not yet held | Not yet held | Not yet awraded
February
| SCM/MOH/04/2020 | Disposal of Municipal Assets | 07/02/2020 | 18/02/2020: Zastron, 20/02/2020: Smithfield, | 26/02/2020 |  | Not yet held | Not yet held | Not yet awarded
| SCM/MOH/05/2020 | Preparation of Fixed Assets Register, Investment Property Register, Landfil Calculations and Actuarial Variation | 28/02/2020 | 09/03/2020 | 20/03/2020 | 27/02/2020 | 08/07/2020 | 15/07/2020 | 15/07/2020 | EMS Solutions | 1306941.91
March
No Bids advertised
April
No Bids advertised
May
No Bids advertised
June
No Bids advertised
Notes:
1. SCM numbers in between will be found in the RFQ register.
| Prepared by: …………………………………………… |  |  | Reviewed by: …………………………………………… |  |  |  |  | Final Review by: ……………………………………………
| P.G Lesenyeho |  |  | E Wilken |  |  |  |  | P Dyonase
| Acting: SCM Accountant |  |  | Senior Manager: Financial Services |  |  |  |  | Chief Financial Officer