## 1200A
CLIENT: |  | MOHOKARE LOCAL MUNICIPALITY
CONTRACT NO: |  | SCM/MOH/01/2025
CONTRACT |  | RE-ADVERT: APPOINTMENT OF A CONTRACTOR:CONSTRUCTION OF THE
TITLE: |  | ROUXVILLE SPORTS GROUND (PHASE 1)
BILL OF QUANTITIES
NB | TENDERERS MUST COMPLETE THE SCHEDULE OF QUANTITIES IN BLACK INK
SECTION 1200 A
PAYMENT
REFERS | ITEM |  |  | DESCRIPTION | UNIT | QUAN- | RATE | AMOUNT
TO | NO |  |  |  |  | TITY
SANS | 110.00 | GENERAL
1200 A
8.3 | 110.01 | SCHEDULED FIXED-CHARGE
AND VALUE-RELATED ITEMS
PSA |  | .01 | Fixed preliminary and general |  | Sum | 1 | Sum
8.3.1 |  |  | charges
PSA |  | .02 | Value related preliminary and |  | Sum | 1 | Sum
8.3.2 |  |  | general charges
| 110.02 | Scheduled time-related items:
PSA |  | .01 | Time-related preliminary and
8.4.1 |  |  | general charges |  | - | - | Sum
| 110.03 | Sums stated provisionally by
Engineer:
PSA |  | .01 | Works executed by the
8.5.1 |  |  | Contractor:
|  |  | .01 | General refurbishment work | - | Prov | Sum | 10000
|  | .02 | Overheads, charges and profit
on subitem 110.03.01.01
|  |  | above |  | % | 10000
|  | .03 | Works executed by
Sub-Contractors:
|  |  | .01 | Drilling, Testing and Equipping
of borehole (including all
|  |  |  | relevant pipe fittings, | - | Prov | Sum | 150000
casing, etc.)
|  |  | .02 | Overheads, charges and
profit on subitem
|  |  |  | 110.03.03.01 | % | 150000
1200 A | Carried forward
SECTION 1200 A
PAYMENT
REFERS | ITEM |  |  | DESCRIPTION | UNIT | QUAN- | RATE | AMOUNT
TO | NO |  |  |  |  | TITY
Brought forward
|  | .04 | Maintenance of kikuyu grass |  | - | Prov | Sum | 30000
during the construction period
|  |  | .01 | Overheads, charges and profit
|  |  |  | on subitem 110.03.04.01 | % | 30000 | 5% | 1500
above
PSA | 110.04 | Prime Cost Sums:
8.6
|  | .01 | Additional tests required by the
|  |  | Engineer |  | - | - | PC Sum | 2500
|  | .02 | Charge required by Contractor
|  |  | on subitem 110.04.01 above |  | % | 2500
|  | .03 | Housing for Engineer's |  | - | - | PC Sum | 15000
representative
|  | .04 | Charge required by Contractor
|  |  | on subitem 110.04.03 above |  | % | 15000
|  | .05 | Transportation for the Engineer |  | - | - | PC Sum | 10000
|  | .06 | Charge required by Contractor
|  |  | on subitem 110.04.05 above |  | % | 10000
|  | .07 | Telephone costs for the Engineer |  | - | - | PC Sum | 5000
|  | .08 | Charge required by Contractor
|  |  | on subitem 110.04.05 above |  | % | 5000
PSA | 110.05 | Daywork (Provisional)
8.7
|  | .01 | Labour
|  |  | .01 | Skilled labour | h | 8
|  |  | .02 | Semi-skilled labour | h | 8
|  |  | .03 | Unskilled labour | h | 8
|  | .02 | Materials
|  |  | .01 | Allow for all-inclusive materials
|  |  |  | actually used | - | - | PC Sum | 2500
|  |  | .02 | Charge required by Contractor
|  |  |  | on subitem 110.05.02.01 above | % | 2500
1200 A | Carried forward
SECTION 1200 A
PAYMENT
REFERS | ITEM |  |  | DESCRIPTION | UNIT | QUAN- | RATE | AMOUNT
TO | NO |  |  |  |  | TITY
Brought forward
PSA |  | .03 | Contractor's own Plant
8.7
|  |  | .01 | Allow for all-inclusive cost of
|  |  |  | using Contractor's own plant on | - | - | PC Sum | 5000
Site
|  |  | .02 | Charge required by Contractor
|  |  |  | on subitem 110.05.03.01 above | % | 5000
|  | .04 | Plant hired by the Contractor
|  |  | .01 | Allow for net cost of hired plant | - | - | PC Sum | 5000
|  |  | .02 | Charge required by Contractor
|  |  |  | on subitem 110.05.04.01 above | % | 5000
PSA 8.9 | 110.06 | Compliance with OHS Act and
|  | Construction Regulations: |  |  | - | - | sum
SDA | 110.08 | Local Subcontrators Compliance
8.9 |  | with OHS Act and Construction
|  | Regulations: |  |  | - | - | sum
| 110.07 | Community Liaison Officer
|  | .01 | Community Liaison Officer Cost |  | months |  | 6000
|  | .02 | Project Steering Committee costs |  | PC Sum | 1 | 5250 | 5250
(R350 per member per sitting)
|  | .03 | Overheads, charges and profit on
|  |  | subitem 110.09.01 above |  | %
SDAB | 110.08 | Name Board
8.2.6
|  | .01 | Supply and install project
nameboard as per specifications
and at location specified by
|  |  | Employer |  | - | Prov | Sum | 15000
SDA 8.11 | 110.09 | Training
|  | .01 | Allow for cost of training |  | - | - | PC Sum | 25000
|  | .02 | Percentage adjustment on Item
110.12.01 for Contractor's
|  |  | overheads and profit |  | % | 25000
1200 A | TOTAL OF SECTION 1200 A CARRIED TO SUMMARY

## 1200C
SECTION 1200 C
PAYMENT
REFERS | ITEM |  |  | DESCRIPTION | UNIT | QUAN- | RATE | AMOUNT
TO | NO |  |  |  |  | TITY
SABS | 130.00 | SITE CLEARANCE
1200 C
PSC | 130.01 | Clear and grub:
8.2.1
|  | .01 | Areas |  | m² | 17000
TOTAL SECTION 1200 C CARRIED TO SUMMARY

## 1200D
SECTION 1200 D
PAYMENT
REFERS | ITEM |  |  | DESCRIPTION | UNIT | QUAN- | RATE | AMOUNT
TO | NO |  |  |  |  | TITY
SABS | 140.00 | EARTHWORKS
1200 D
PSD | 140.01 | Bulk excavation:
8.3.2
|  | .01 | Excavate in all materials and use for
embankment or backfill as ordered
from:
|  |  | .01 | Necessary excavations | m³ | 200
|  |  | .02 | Cut to fill compacted to 93% of
|  |  |  | modified AASHTO maximum | m³ | 400
density
|  | .02 | Excavate in all materials and dispose |  | m³ | 50
|  | .03 | Extra over items 140.01.01,
140.01.01.01 and 140.01.02 above for:
|  |  | .01 | Intermediate excavation | m³ | 45
|  |  | .02 | Hard rock excavation | m³ | 15
8.3.4 | 140.03 | Importing of materials:
|  | .01 | Extra over items 140.01 for importation
|  |  | of G6 material from commercial sources |  | m³ | 50
PSD | 140.07 | Existing services:
8.3.8
|  | .01 | Hand excavation for locating and
exposing existing services:
|  |  | .01 | In all other areas | m³ | 10
SDD | 140.14 | Extra over items 140.01.01 for Backfill
8.3.9 |  | or for fill materials against structures
|  | .01 | Construct in 150mm layers
G6 material from commercial sources
as per drawings
|  |  | .01 | G6 Material | m³ | 50
SDDM | 140.10 | Treatment of insitu material:
8.3.3
|  | .03 | Rip and re-compact insitu material
compacted to 93% MOD AASHTO
|  |  | .01 | Soccer Pitch | m² | 8900
1200 D | Carried forward
SECTION 1200 D
PAYMENT
REFERS | ITEM |  |  | DESCRIPTION | UNIT | QUAN- | RATE | AMOUNT
TO | NO |  |  |  |  | TITY
Brought forward
SDME | 140.11 | Construct the subbase course with
8.3.3 |  | material from commercial sources
|  | .01 | 100 mm Thick Fertilised, weed free |  | m³ | 890
Topsoil Material for Grassing
|  | .02 | 15mm Thick Fertilised, weed free
|  |  | Sieved Topsoil Material for Grassing |  | m³ | 120
8.3.9 | 140.12 | Extra-over for backfill or fill material against
|  | structure |  |  | m³ | 50
SDD | 140.13 | Supply, deliver and Install Instant Lawn
8.3.16 |  | (Kikuyu) estabishment (per drawing no: |  |  | m² | 8900
(Drawing No: 1109-CIV-DRG-400)
SDDM | 140.14 | Field markings (refer to drawwing |  |  | sum | 1
8.3.17 |  | 1109-CIV-DRG-400)
TOTAL SECTION 1200 D CARRIED TO SUMMARY

## 1200DB
SECTION 1200 DB
PAYMENT
REFERS | ITEM |  |  | DESCRIPTION | UNIT | QUAN- | RATE | AMOUNT
TO | NO |  |  |  |  | TITY
SABS | 142.00 | EARTHWORKS (PIPE TRENCHES)
1200 DB
TRENCHES FOR WATER PIPES
PSDB | 142.01 | Excavate in all materials for trenches,
8.3.2 |  | backfill, compact and dispose of
surplus material:
|  | .01 | Pipes up to 150 mm dia for depths:
|  |  | .01 | Up to 1,0 m | m | 400
|  |  | .02 | Over 1,2 to 2,0 m | m | 100
PSDB | 142.02 | Extra over item 142.01 above for:
8.3.2
|  | .01 | Intermediate excavation |  | m³ | 20
|  | .02 | Hard rock excavation |  | m³ | 10
|  | .03 | Backfill stabilized with 5% cement
|  |  | where directed by the Engineer |  | m³ | 5
PSDB | 142.07 | Excavate for stormwater inlet and
8.3.2 |  | outlet structures and for manholes,
catchpits and the like in all materials,
|  | irrespective of depth and backfill |  |  | m³ | 5
around structures
PSDB | 142.08 | Accommodation of traffic
8.3.7
|  | .01 | Adjacent Street |  | sum | 1
TOTAL SECTION 1200 DB CARRIED TO SUMMARY

## 1200G
SECTION 1200 G
PAYMENT
REFERS | ITEM |  |  | DESCRIPTION | UNIT | QUAN- | RATE | AMOUNT
TO | NO |  |  |  |  | TITY
SABS | 170.00 | CONCRETE (STRUCTURAL)
1200 G
SCHEDULED FORMWORK ITEMS
8.2.5 | 170.02 | Smooth:
|  | .01 | Vertical formwork to:
|  |  | .01 | Narrow sections 200 mm to 400 mm deep | m | 20
8.2.5 |  | SCHEDULED REINFORCEMENT ITEMS
8.3.2 | 170.07 | High-tensile welded mesh in the
following:
|  | .01 | Mesh Ref No.193 in surface bed |  | m² | 20
8.3.1 |  | SCHEDULED CONCRETE ITEMS
8.4.2 | 170.06 | .02 | Concrete Grade 25 MPa/20 mm to:
|  |  | .01 | Slabs | m³ | 5
| 170.07 | Unformed surface finishes:
|  | .01 | Steel-floated finishes to:
|  |  | .01 | Top of slabs | m² | 20
SDG 8.5 | 170.11 | Joints:
|  | .01 | Saw Cut Joint |  | m | 10
| 1200 G | TOTAL OF SECTION 1200 G CARRIED TO SUMMARY

## 1200H
SECTION 1200 H
PAYMENT
REFERS | ITEM |  |  | DESCRIPTION | UNIT | QUAN- | RATE | AMOUNT
TO | NO |  |  |  |  | TITY
SABS | 180.00 | STRUCTURAL STEELWORK
1200 H
SD8.3.17 | 180.17 | Structural steel posts
(Drawing No: 1109-CIV-DRG-401)
|  | .01 | Complete prefabricated soccer and |  | No. | 2
rugby posts with nets
TOTAL SECTION 1200 H CARRIED TO SUMMARY

## 1200L
SECTION 1200 L
PAYMENT
REFERS | ITEM |  |  | DESCRIPTION | UNIT | QUAN- | RATE | AMOUNT
TO | NO |  |  |  |  | TITY
SABS | 210.00 | MEDIUM-PRESSURE PIPELINES
1200 L
8.2.1 | 210.01 | Supply, lay and bed on flexible
bedding, complete with couplings:
|  | .01 | PVC-u class 9 pipes:
|  |  | .01 | 75mm diameter | m | 150
|  | .02 | HDPE class 6 pipes: complete with
fiitings as per drawing:
(1109-CIV-DRG-200)
|  |  | .01 | 50mm diameter | m | 410
| 210.02 | Supply, lay and bed on flexible
bedding, complete with couplings:
Steel Pipe:
(at road crossings)
|  | .01 | 75mm diameter (Grade x42 steel) -
|  |  | 5.0mm wall thickness |  | m | 20
8.2.2 | 210.03 | Extra over items 210.01 for
supplying, laying and bedding of
PVC-u and HDPE specials complete
with couplings:
|  | .01 | 90° elbows:
|  |  | .01 | DN50 mm | No. | 2
|  |  | .02 | DN75 mm | No. | 2
|  | .02 | Tees:
|  |  | .01 | 75 mm x 75 mm dia | No, | 1
|  | .03 | Reducing tees:
|  |  | .02 | DN90 mm x DN90 mm x DN75 mm | No. | 1
|  | .04 | End caps
|  |  | .01 | DN 75 mm | No. | 1
|  | .05 | PVC-u flanged adaptor Couplings
|  |  | .01 | DN 50mm | No. | 2
|  |  | .02 | DN 75mm | No. | 1
1200 L | Carried forward
SECTION 1200 L
PAYMENT
REFERS | ITEM |  |  | DESCRIPTION | UNIT | QUAN- | RATE | AMOUNT
TO | NO |  |  |  |  | TITY
Brought forward
|  | .06 | Reducer
|  |  | .01 | DN 75 x 50mm PVC-u Reducer | No. | 2
PSL | 210.04 | Anchor/thrust blocks and pedestals:
8.2.11
|  | .01 | Concrete:
|  |  | .01 | Class 20 MPa/19 mm | m³ | 1
SDL | 210.06 | Irrigation Connection Point
8.2.12 |  | (Drawing No. 1109-CIV-DRG-200) |  |  | No. | 4
SDL | 210.07 | Movable Impact Sprinkler
8.2.13 |  | (Drawing No. 1109-CIV-DRG-200 ) |  |  | No. | 2
PSL | 210.08 | Irrigation Pumps
8.2.14
|  | .01 | 2.5kw Booster Irrigation pump |  | Sum | 1
|  | .02 | 2.2kw borehole suction pump |  | Sum | 1
|  | .03 | Charge required by Contractor on
|  |  | subitem 210.68.01&02 above |  | % | 5%
PSL | 210.05 | Valve and Hydrant Chamber
8.2.13
|  | .01 | Fire Hydrant and Stand post as per
|  |  | drawing (Drawing No.1109-CIV-DRG-201) |  | No. | 1
|  | .02 | Water Meter Chamber as per drawing
|  |  | (Drawing No.1109-CIV-DRG-201) |  | No. | 1
| 210.70 | 2 x 10000l JoJo tanks complete with
fittings, valves and pipe work
|  | .01 | Prime Cost Sums: |  | - | - | PC Sum | 25000
|  | .02 | Charge required by Contractor on
|  |  | subitem 210.68.01 above |  | % | 20000
TOTAL SECTION 1200 L CARRIED TO SUMMARY

## 1200LB
SECTION 1200 LB
PAYMENT
REFERS | ITEM |  |  | DESCRIPTION | UNIT | QUAN- | RATE | AMOUNT
TO | NO |  |  |  |  | TITY
SABS | 211.00 | BEDDING (PIPES)
1200 LB
8.2.1 | 211.01 | Provision of bedding from trench
excavations:
|  | .01 | Selected granular material |  | m³ | 70
|  | .02 | Selected fill material |  | m³ | 100
PSLB | 211.02 | Supply only of bedding by
8.2.2 |  | importation:
|  | .03 | From commercial sources:
|  |  | .01 | Selected granular material | m³ | 10
|  |  | .02 | Selected fill material | m³ | 10
8.2.4 | 211.03 | Encasing of pipes in concrete:
|  | .01 | Class 25 MPa/19 mm |  | m³ | 1
TOTAL SECTION 1200 LB CARRIED TO SUMMARY

## 1200LK
SECTION 1200 LK
PAYMENT
REFERS | ITEM |  |  | DESCRIPTION | UNIT | QUAN- | RATE | AMOUNT
TO | NO |  |  |  |  | TITY
(SPEC LK) | 220.00 | VALVE INSTALLATIONS
PSLK 8.2.1 | 220.01 | Supply and deliver valve:
|  | .01 | Gate Valve
flanged/threaded valves with
non-rising spindles,complete with
handwheel, complete with coupling
|  |  | .01 | DN 50mm PN 10 | No | 1
|  |  | .02 | DN 75mm PN 10 | No | 3
Magflow watermeter
|  | .02 | Mechanical Watermeter
|  |  | .01 | DN 75mm PN 10nElster Kent
|  |  |  | "Helix 4000" watermeter | No. | 1
|  | .03 | Strainer
|  |  | .01 | DN 75 mm PN 10 Elster Kent | No. | 1
Helix 4000
SDLK 8.2.2 | 520.02 | Install, bed and field-test small valve
(nominal bore up to 300mm)
|  | .01 | GateValves
|  |  | .01 | DN 50mm PN 10 | No | 1
|  |  | .02 | DN 75mm PN 10 | No | 1
|  | .02 | Mechanical Water Meter
|  |  | .01 | DN 75mm PN 10 | No. | 1
|  | .03 | Strainer
|  |  | .01 | DN 75 mm PN 10 | No. | 1
TOTAL SECTION 1200 LK CARRIED TO SUMMARY

## 1200ME (hidden)
SECTION 1200 ME
PAYMENT
REFERS | ITEM |  |  | DESCRIPTION | UNIT | QUAN- | RATE | AMOUNT
TO | NO |  |  |  |  | TITY
SABS | 223.00 | SUBBASE
1200 ME
PSME | 223.07 | Construct the subbase course with
8.3.3 |  | material from commercial sources
|  | .01 | G6 Material |  | m³ | 0 | 280 | 0
| TOTAL SECTION 1200 ME CARRIED TO SUMMARY | [6 empty] | 0

## 1200MF (hidden)
SECTION 1200 MF
PAYMENT
REFERS | ITEM |  |  | DESCRIPTION | UNIT | QUAN- | RATE | AMOUNT
TO | NO |  |  |  |  | TITY
SABS | 224.00 | BASE
1200 MF
8.3.3 | 224.03 | Construct base with material from
commercial sources or designated
borrow areas:
72
|  | .01 | Sand |  | m³ | 160 | 280 | 44800
| TOTAL SECTION 1200 MF CARRIED TO SUMMARY | [6 empty] | 0

## 1200MK
SECTION 1200 MK
PAYMENT
REFERS | ITEM |  |  | DESCRIPTION | UNIT | QUAN- | RATE | AMOUNT
TO | NO |  |  |  |  | TITY
SABS | 228.00 | KERBING AND CHANNELLING
1200 MK
PSMK | 228.01 | Pre-cast Figure 12 kerbing:
8.2.1
|  | .01 | Grade 20 concrete:
|  |  | .03 | Radius over straight
|  |  |  | sections | m | 450
TOTAL SECTION 1200 MK CARRIED TO SUMMARY

## PART PA
PARTICULAR SPECIFICATION PA
PAYMENT
REFERS | ITEM |  |  | DESCRIPTION | UNIT | QUAN- | RATE | AMOUNT
TO | NO |  |  |  |  | TITY
PA 12 |  | FENCING
| PA.01 | Supply and erection of new 2.4 m high
Clear -vu fencing
|  | .01 | Complete Clearvu fence with posts, |  | m | 550
clamps, bolts and concrete footings
Refer No.1109-CIV-DRG-502
| PA.02 | New gates:
|  | .01 | 1.2m pedestrian Clear Vu gate
complete with posts, hinges and
|  |  | locking mechanisim Refer to drawing |  | No. | 1
No.1109-CIV-DRG-501
|  | .02 | Complete Clearvu single leaf Sliding
|  |  | gate Refer to drawing |  | No. | 2
Refer No.1109-CIV-DRG-502
TOTAL PARTICULAR SPECIFICATION PA CARRIED TO SUMMARY

## SUMMARY
EMPLOYER : | MOHOKARE LOCAL MUNICIPALITY
CONTRACT NO : | SCM/MOH/01/2025
CONTRACT TITLE : | RE-ADVERT: APPOINTMENT OF A CONTRACTOR:CONSTRUCTION OF THE
ROUXVILLE SPORTS GROUND (PHASE 1)
SUMMARY OF SCHEDULE OF QUANTITIES
Tendered Amount
SECTION 1200 A |  | R | 0
SECTION 1200 D |  | R | 0
SECTION 1200 C |  | R | 0
SECTION 1200 D |  | R
SECTION 1200 DB |  | R | 0
SECTION 1200 G |  | R | 0
SECTION 1200 H |  | R | 0
SECTION 1200 L |  | R | 0
SECTION 1200 LB |  | R | 0
SECTION 1200 LK |  | R | 0
SECTION 1200 MK |  | R | 0
PARTICULAR SPECIFICATION PA |  | R | 0
SUB TOTAL |  | R | 0
CONTINGENCIES (5%)
The Sum provided here is under the sole control of the Engineer and may
be deducted in whole or in part |  | R
SUB TOTAL (Excl.Vat) |  | R
VALUE ADDED TAX (VAT)
The tenderer shall add 15% of the subtotal for value-added tax |  | R
TENDER SUM CARRIED TO FORM OF OFFER AND ACCEPTANCE |  | R
SIGNED ON BEHALF OF TENDERER: . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .